## How to use this
What this is: A list of key decisions for your AI program and a place to clarify who owns, contributes to, and stays informed about each one.
How to fill it in: Complete it with your executive sponsor and IT counterpart, and allow about an hour. Expect some disagreement. Working through those differences now can surface questions about ownership and decision-making before they become blockers.
R | Responsible – Does the work. More than one person can be responsible.
A | Accountable – Ultimately answerable for the outcome. Assign one person only.
C | Consulted – Provides input before the decision is made.
I | Informed – Kept informed about the decision and its outcome.
The rule that matters: Assign one accountable person per row. If you find yourself with two, clarify who has final accountability. If you have none, assign an owner before moving forward.

## The RACI
Decision | AI leader | Executive sponsor | IT | Security & compliance | Business owner | AI Champion | Finance
Set priority business outcomes | [7 empty] | R | Responsible
Select first-wave workflows | [7 empty] | A | Accountable
Approve the program budget | [7 empty] | C | Consulted
Approve tools and providers | [7 empty] | I | Informed
Provision licenses and access
Set data permissions and governance
Provide security and compliance approval
Own the outcome of a live workflow
Define success metrics and baselines
Report business impact to leadership
Decide whether to scale, rework, or stop a workflow
Own an agent and its permissions
Lead enablement and training
Communicate change to employees

## Worked example
Decision | AI leader | Executive sponsor | IT | Security & compliance | Business owner | AI Champion | Finance
Set priority business outcomes | R | A | C | I | C | I | C
Select first-wave workflows | A | C | C | I | R | C | I
Approve the program budget | C | A | C | I | C | I | R
Approve tools and providers | C | C | A | C | I | I | I
Provision licenses and access | I | I | A/R | C | C | I | I
Set data permissions and governance | C | I | R | A | C | I | I
Provide security and compliance approval | C | I | C | A/R | I | I | I
Own the outcome of a live workflow | C | I | I | I | A/R | C | I
Define success metrics and baselines | A | C | C | I | R | I | C
Report business impact to leadership | A/R | C | I | I | C | I | C
Decide whether to scale, rework, or stop a workflow | R | A | C | I | C | I | C
Own an agent and its permissions | C | I | R | C | A | I | I
Lead enablement and training | C | I | C | I | C | A/R | I
Communicate change to employees | C | A | I | I | R | R | I

## Decisions to revisit
Some decisions may need more time to resolve. Add them here rather than leaving them blank, and give each one an owner and a date. Revisit them at your next review. Capturing them now ensures they don't get lost.
Decision | AI leader | Executive sponsor | IT | Security & compliance | Business owner | AI Champion | Finance