## Slide 1
OneDrive Adoption Campaign Project Plan Template

## Slide 2
Pre-Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Status
Week 1 | Stakeholders | Assign Success Owner/Project Manager |  |  | 
 | Project Management | Conduct workshop using OneDrive Adoption Playbook to review best practices for successful adoption of OneDrive |  |  | 
 |  | Develop adoption campaign project plan using this deck to develop a week-by-week plan. |  |  | 
Week 2 | Stakeholders | Identify and recruit Executive Sponsor and Business Sponsors |  |  | 
 | Scenarios | Identify and prioritize Usage Scenarios for OneDrive. Define success criteria for OneDrive adoption campaign. |  |  | 
 | Awareness | Develop OneDrive launch/engagement event(s) strategy |  |  | 
 | Technology | Assess Known Folder Move (KFM) and plan implementation |  |  | 
 | Project Management | Weekly status meeting: review OneDrive adoption campaign project plan |  |  | 
Week 3 | Stakeholders | Plan executive sponsor communications using Executive Communication Planning presentation |  |  | 
 | Awareness | Prepare communication materials (e.g., pre-launch email, launch email, tips and tricks, etc.) |  |  | 
 | Training | Plan end-user training program using Training Plan template |  |  | 
 | Early Adoption Program | Begin Early Adoption Program by recruiting and training program participants. Learn more with the Early Adoption Program Guide. Running this program allows you to gather feedback on the user's launch experience and get early success stories that can be used when launching OneDrive across your organization. |  |  | 
 | Project Management | Weekly status meeting: Review executive/business sponsor recruitment, scenario prioritization and success criteria status Review communication plan and launch/buzz event strategy |  |  | 

## Slide 3
Pre-Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Status
Week 4 | Stakeholders | Plan OneDrive champions program using Champion Program template |  |  | 
 | Awareness | Send a “Teaser email" using OneDrive Countdown Email template to let employees know what's coming, set expectations, and spark interest by focusing on the "What's in it for me?" |  |  | 
 | Training | Set up an internal SharePoint Communication site to store training resources such as the OneDrive Quick Start Guide and tips & tricks. Direct users to OneDrive’s learning center. |  |  | 
 | Early Adoption Program | Check in with Early Adoption Program participants for feedback and recruit participants into champions program |  |  | 
 | Project Management | Weekly status meeting: Review status of executive/business sponsor progress Review training plan |  |  | 
Week 5 | Awareness | Work with internal communications to make announcements across company portal, IT portal, and other internal sites as needed |  |  | 
 |  | Prepare for launch/engagement event |  |  | 
 |  | Ensure that OneDrive has a visual presence throughout offices with posters, flyer, and teaser videos (using OneDrive excitement video one, two and three) |  |  | 
 | Training | Ready help desk to support end-users, and make sure they know about the M365 Troubleshooting Guide for Admins and the OneDrive for business troubleshooting guide. |  |  | 
 |  | Conduct “Train-the-trainer” sessions using the OneDrive End User Training presentation |  |  | 
 | Early Adoption Program | Assess if any changes to adoption campaign plan or materials are necessary based on feedback from early adoption program participants |  |  | 
 | Project Management | Weekly status meeting: Review status of champion program, communications, launch/buzz event preparation |  |  | 
Week 6 | Training | Conduct champion training using the OneDrive Champion Training presentation |  |  | 
 |  | Conduct end user training using OneDrive End User Training presentation |  |  | 
 | Project Management | Weekly status meeting: Review action items and status |  |  | 

## Slide 4: Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Status
Week 7 | Awareness | Send out an "Announcement email" using the OneDrive Announcement email for sales and marketing template to let users know what's available, how to get started, and where to go to find help and resources |  |  | 
 |  | Execute OneDrive launch event to excite end users |  |  | 
 | Training | Conduct end-user training using the OneDrive video training |  |  | 
 | Project Management | Weekly status meeting: review of launch activities and their impact |  |  | 

## Slide 5: Post-Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Owner
Week 8-12 | Awareness | Run an end user "Tips Campaign“, using Tips to Access and Find Files Email template and Tips to Share & Collaborate Email template, to sustain momentum and broaden the use of OneDrive |  |  | 
 |  | Prepare and run contests to continue encouraging user engagement Periodically host additional engagement events (e.g., lunch and learns) |  |  | 
 | Stakeholder | Get feedback from Champions and iterate program as necessary |  |  | 
 | Training | Continue ongoing end-user training series as applicable |  |  | 
 | Measurement | Collect and report on OneDrive adoption campaign success criteria Report on OneDrive usage in organization since start of end user adoption campaign: Basic OneDrive usage reports available in the admin center: Instructions on how to access and interpret the report are here Microsoft 365 Usage Analytics: More robust and insightful usage reports - see overview here. You can visualize and analyze Office 365 (i.e., OneDrive) usage data, create custom reports and share the insights within your organization and gain insights into how specific regions or departments are utilizing Office 365 (i.e., OneDrive). |  |  | 
 | Project Management | Post launch meeting(s): Review usage levels Review success criteria results Identify additional engagement activities to increase usage levels |  |  |