## Slide 1
SharePoint Adoption Campaign Project Plan Template

## Slide 2
Pre-Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Status
Week 1 | Stakeholders | Assign Success Owner/Project Manager |  |  | 
 | Project Management | Conduct workshop using SharePoint Adoption Playbook to review best practices for successful adoption |  |  | 
 | Project Management | Develop adoption campaign project plan using SharePoint Adoption Campaign Project Plan template |  |  | 
Week 2 | Stakeholders | Identify and recruit Executive Sponsor and Business Sponsors |  |  | 
 | Scenarios | Identify and prioritize Usage Scenarios for SharePoint. Define success criteria for SharePoint adoption campaign. |  |  | 
 | Awareness | Develop communications plan using Communication Plan template |  |  | 
 | Awareness | Develop SharePoint launch/engagement event(s) strategy |  |  | 
 | Project Management | Weekly status meeting: review SharePoint adoption campaign project plan |  |  | 
Week 3 | Stakeholders | Plan executive sponsor communications using Executive Communication Planning presentation |  |  | 
 | Awareness | Prepare communication materials (e.g., pre-launch news post, launch news post, tips and tricks, etc.) |  |  | 
 | Training | Plan end-user training program using Training Plan template |  |  | 
 | Early Adoption Program | Begin Early Adoption Program by recruiting and training program participants. Learn more with the Early Adoption Program Guide Running this program allows you to gather feedback on the user's launch experience and get early success stories that can be used when launching SharePoint across your organization. |  |  | 
 | Project Management | Weekly status meeting: Review executive/business sponsor recruitment, scenario prioritization and success criteria status Review communication plan and launch/buzz event strategy |  |  | 

## Slide 3
Pre-Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Status
Week 4 | Stakeholders | Plan SharePoint champions program using Champion Program template |  |  | 
 | Awareness | Send a “Teaser" news post using SharePoint Countdown template to let employees know what's coming, set expectations, and spark interest by focusing on the "What's in it for me?" |  |  | 
 | Training | Deploy the Microsoft 365 learning pathways training solution to store training resources such as the SharePoint Quick Start Guide and tips & tricks. |  |  | 
 | Early Adoption Program | Check in with Early Adoption Program participants for feedback and recruit participants into champions program |  |  | 
 | Project Management | Weekly status meeting: Review status of executive/business sponsor progress Review training plan |  |  | 
Week 5 | Awareness | Work with internal communications to make announcements across company portal, IT portal, and other internal sites as needed |  |  | 
 |  | Prepare for launch/engagement event |  |  | 
 |  | Ensure that SharePoint has a visual presence throughout offices with posters and flyers |  |  | 
 | Training | Conduct “Train-the-trainer” sessions using the SharePoint End User Training presentation |  |  | 
 | Early Adoption Program | Assess if any changes to adoption campaign plan or materials are necessary based on feedback from early adoption program participants |  |  | 
 | Project Management | Weekly status meeting: Review status of champion program, communications, launch/buzz event preparation |  |  | 
Week 6 | Training | Conduct champion training using the SharePoint End User Training presentation |  |  | 
 |  | Conduct end user training using SharePoint End User Training presentation |  |  | 
 | Project Management | Weekly status meeting: Review action items and status |  |  | 

## Slide 4: Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Status
Week 7 | Awareness | Send out an "Announcement" news post using the SharePoint Announcement template to let users know what's available, how to get started, and where to go to find help and resources |  |  | 
 |  | Execute SharePoint launch event to excite end users |  |  | 
 | Training | Conduct end-user training using the SharePoint End User Training presentation |  |  | 
 | Project Management | Weekly status meeting: review of launch activities and their impact |  |  | 

## Slide 5: Post-Launch
Timeline | Workstream | Description | Owner(s) | Due Date | Owner
Week 8-12 | Awareness | Run an end user "Tips Campaign“, using the Tips and Tricks news post template, to sustain momentum and broaden the use of SharePoint |  |  | 
 |  | Prepare and run contests to continue encouraging user engagement Periodically host additional engagement events (e.g., lunch and learns) |  |  | 
 | Stakeholder | Get feedback from Champions and iterate program as necessary |  |  | 
 | Training | Continue ongoing end-user training series as applicable |  |  | 
 | Measurement | Collect and report on SharePoint adoption campaign success criteria Report on SharePoint usage in organization since start of end user adoption campaign: Basic SharePoint usage reports available in the admin center: Instructions on how to access and interpret the reports are here Microsoft 365 Usage Analytics: More robust and insightful usage reports - see overview here. You can visualize and analyze Office 365 (i.e., SharePoint) usage data, create custom reports and share the insights within your organization and gain insights into how specific regions or departments are utilizing Office 365 (i.e., SharePoint). |  |  | 
 | Project Management | Post launch meeting(s): Review usage levels Review success criteria results Identify additional engagement activities to increase usage levels |  |  |