## RoB - CY23
OKR Workback Schedule - CY23
January | [6 empty] | February | [6 empty] | March | [6 empty] | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |  |  | 2023-02-01 | Monthly Review (January)
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  | 1 | 2 | 3 | 4 |  |  |  | 1 | 2 | 3 | 4 |  |  | 2023-03-02 | Monthly Review (February)
8 | 9 | 10 | 11 | 12 | 13 | 14 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  | 2023-03-03 | LT Offsite: Q2 OKR Planning
15 | 16 | 17 | 18 | 19 | 20 | 21 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  |  | 3/6-3/17 | Dept. Level Q2 Planning
22 | 23 | 24 | 25 | 26 | 27 | 28 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  |  | 2023-03-23 | Quarterly Planning Review
29 | 30 | 31 |  |  |  |  | 26 | 27 | 28 |  |  |  |  | 26 | 27 | 28 | 29 | 30 | 31 |  |  |  | 2023-03-30 | All plans in VG and Finalized
April | [6 empty] | May | [6 empty] | 26: June |  | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |  |  | 2023-04-06 | Quarterly Review (Q1 CY23)
[6 empty] | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  | 1 | 2 | 3 |  |  | 2023-05-04 | Monthly Review (April)
2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2023-06-07 | Monthly Review (May)
9 | 10 | 11 | 12 | 13 | 14 | 15 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  |  | 2023-06-08 | LT Offsite: Q3 OKR Planning
16 | 17 | 18 | 19 | 20 | 21 | 22 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  |  | 6/12-6/23 | Dept. Level Q3 Planning
23 | 24 | 25 | 26 | 27 | 28 | 29 | 28 | 1: 29; 2: 30; 3: 31 | 25 | 26 | 27 | 28 | 29 | 30 |  |  |  | 2023-06-29 | Q1 FY24 Quarterly Planning Review
30 | [22 empty] | 2023-06-30 | All plans in VG and Finalized
July | [6 empty] | August | [6 empty] | September | [6 empty] | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | 7/1-7/9 | Jane | 2023-07-13 | Quarterly Review (Q2 CY23)
[6 empty] | 1 |  |  | 1 | 2 | 3 | 4 | 5 | [5 empty] | 1 | 2 | 7/24-8/11 | Jeff | 2023-08-03 | Monthly Review (July)
2 | 3 | 4 | 5 | 6 | 7 | 8 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | 2023-09-06 | Monthly Review (August)
9 | 10 | 11 | 12 | 13 | 14 | 15 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 2023-09-07 | LT Offsite - Q3 CY23 Planning
16 | 17 | 18 | 19 | 20 | 21 | 22 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  |  | 9/11-9/22 | Q4 CY24 Planning
23 | 24 | 25 | 26 | 27 | 28 | 29 | 27 | 28 | 29 | 30 | 31 |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  | 2023-09-28 | Quarterly Planning Review
30 | 31
October | [6 empty] | November | [6 empty] | December | [6 empty] | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |  |  | 2023-10-05 | Quarterly Review (Q3 CY23)
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  | 1 | 2 | 3 | 4 | [5 empty] | 1 | 2 |  |  | 2023-11-09 | Monthly Review (October)
8 | 9 | 10 | 11 | 12 | 13 | 14 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | 2023-12-06 | Monthly Review (November)
15 | 16 | 17 | 18 | 19 | 20 | 21 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 2023-12-07 | LT Offsite - Q1 CY24 Planning
22 | 23 | 24 | 25 | 26 | 27 | 28 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  |  | 12/11-12/22 | Q4 CY24 Planning
29 | 30 | 31 |  |  |  |  | 26 | 27 | 28 | 29 | 30 |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  | 12/18-12/29 | No Meetings - Winter Break
31
Legend
Non-Working Day
Holiday
Pre-Read Sent (T-3)
Topics Sent (T-1)
Monthly Review Mtg
Quarterly Review Mtg
LT Offsite - Planning
Quarterly Planning - Dept
Planning Review

## Annual Planning - FY24
Annual Planning - FY24 | [25 empty] | Annual Planning - FY24 | Quarterly Planning - Q1
6/8: LT Offsite (Annual Planning/Quarterly Planning)
April | [6 empty] | May | [6 empty] | June | [6 empty] | Out of Office/Vacation |  | Detailed Annual Planning Schedule (4/24-5/25) |  | Notes | 6/29: Q1 Dept. Planning Review
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |  |  | 4/14-5/19 | Memo writing time (5 weeks) | Memos due EoD May 19 | 6/30: All plans in VG and Finalized
[6 empty] | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  | 1 | 2 | 3 |  |  | 2023-04-19 | Joe K check in | ** Jane to send out weekly check-in meetings | 7/11: Townhall
2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2023-04-24 | LT Kick Off - Lunch + 2 hours brainstorming | Outcome: Big bets identified, owners decided and 4 week plan crafted | 7/13: Q4 Closeout meeting
9 | 10 | 11 | 12 | 13 | 14 | 15 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  |  | 2023-04-27 | 90 min check in | report out from Big bet owner
16 | 17 | 18 | 19 | 20 | 21 | 22 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  |  | 2023-05-04 | 90 min check in | report out from Big bet owner
23 | 24 | 25 | 26 | 27 | 28 | 29 | 28 | 1: 29; 2: 30; 3: 31 | 25 | 26 | 27 | 28 | 29 | 30 |  |  |  | 2023-05-04 | Monthly Review (April) |  | Details for Annual Planning 4/24 - 5/25
30 | [22 empty] | 2023-05-11 | 90 min check in | report out from Big bet owner | 4/19 - KirkK check in
[23 empty] | 5/15-5/17 | Daily check in for Plan finalization | Final Deliverable - Memo + PPT for Joe K
July | [6 empty] | August | [6 empty] | September | [6 empty] | Out of Office/Vacation |  | 2023-05-19 | Final Memo to Joe K Due | Memos due EoD May 19 | 4/24 - LT Kick Off - Lunch + 2 hours brainstorming | Outcome: Big bets identified, owners decided and 4 week plan crafted
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | 7/1-7/9 | Jane | 5/22-6/2 | Finalize/Tweak as needed |  | 5/3 - 90 min check in | report out from Big bet owner
[6 empty] | 1 |  |  | 1 | 2 | 3 | 4 | 5 | [5 empty] | 1 | 2 | 7/24-8/11 | Joe | 2023-06-07 | Monthly Review (May) |  | 5/10 - 90 min check in | report out from Big bet owner
2 | 3 | 4 | 5 | 6 | 7 | 8 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | 2023-06-08 | LT Offsite - Q1 FY24 Planning | Finalize Annual & Q1 FY24 OKRs | 5/15 - 17 - Daily check in for KirkK Prep | Final Deliverable - Memo + PPT for Kirk
9 | 10 | 11 | 12 | 13 | 14 | 15 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 2023-06-14 | LT Q1 Planning Review |  | 5/18 - Report out to Kirk
16 | 17 | 18 | 19 | 20 | 21 | 22 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  |  | 6/12-6/23 | Q1 Department Planning |  | 5/15 - Feedback incorporated, Plan finalized
23 | 24 | 25 | 26 | 27 | 28 | 29 | 27 | 28 | 29 | 30 | 31 |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  | 2023-06-29 | Q1 Dept. Planning Review
30 | 31 | [21 empty] | 2023-06-30 | All plans in VG and Finalized
[23 empty] | 2023-07-11 | Townhall | All Annual OKRs are Final here | Apr/14 – kickoff with LT and share plan / template (this email)
Legend | [6 empty] | Planning Legend | [15 empty] | 2023-07-13 | Q4 Closeout meeting |  | Apr/14 – May/19 – Memo writing time (5 weeks); *memos due EoD May/19*
| Non-Working Day | [6 empty] | 1: Non-Working Day | [12 empty] | May/22 – Jun/2 – finalize / tweak as needed
| Holiday | [6 empty] | 1: Holiday
| Pre-Read Sent (T-3) | [6 empty] | 1: Meeting with JoeK
| Topics Sent (T-1) | [6 empty] | 1: Planning Review
| Monthly Review Mtg | [6 empty] | 1: Report Out
| Quarterly Review Mtg | [6 empty] | 1: E+D Meeting
| Quarterly Planning - LT | [6 empty] | 1: Annual Planning - LT
Quarterly Planning - Dept
Apr/14 – kickoff with LT and share plan / template (this email)
Apr/14 – May/19 – Memo writing time (5 weeks); *memos due EoD May/19*
May/22 – Jun/2 – finalize / tweak as needed
Apr/14 – kickoff with LT and share plan / template (this email)
Apr/14 – May/19 – Memo writing time (5 weeks); *memos due EoD May/19*
May/22 – Jun/2 – finalize / tweak as needed

## RoB- FY24
OKR Workback Schedule - FY24
July | [6 empty] | August | [6 empty] | September | [6 empty] | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | 7/1-7/9 | Jane | 2023-06-28 | Annual Planning
[6 empty] | 1 |  |  | 1 | 2 | 3 | 4 | 5 | [5 empty] | 1 | 2 | 7/24-8/11 | Jeff | 2023-07-13 | Quarterly Review (Q4 FY23)
2 | 3 | 4 | 5 | 6 | 7 | 8 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | 2023-08-03 | Monthly Review (July)
9 | 10 | 11 | 12 | 13 | 14 | 15 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 2023-09-06 | Monthly Review (August)
16 | 17 | 18 | 19 | 20 | 21 | 22 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  |  | 2023-09-07 | LT Offsite - Q2 FY24 Planning
23 | 24 | 25 | 26 | 27 | 28 | 29 | 27 | 28 | 29 | 30 | 31 |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  | 9/11-9/22 | Q2 FY24 Planning
30 | 31 | [21 empty] | 2023-09-28 | Quarterly Planning Review
October | [6 empty] | November | [6 empty] | December | [6 empty] | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |  |  | 2023-10-05 | Quarterly Review (Q1 FY24)
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  | 1 | 2 | 3 | 4 | [5 empty] | 1 | 2 |  |  | 2023-11-09 | Monthly Review (October)
8 | 9 | 10 | 11 | 12 | 13 | 14 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | 2023-12-06 | Monthly Review (November)
15 | 16 | 17 | 18 | 19 | 20 | 21 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 2023-12-07 | LT Offsite - Q3 FY24 Planning
22 | 23 | 24 | 25 | 26 | 27 | 28 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  |  | 12/11-12/22 | Q3 FY24 Planning
29 | 30 | 31 |  |  |  |  | 26 | 27 | 28 | 29 | 30 |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  | 12/18-12/29 | No Meetings - Winter Break
31
January | [6 empty] | February | [6 empty] | 24: March | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |  |  | 2023-01-09 | Quarterly Planning Review
| 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  | 1 | 2 | 3 | 29: 1; 30: 2 |  |  | 2023-01-11 | Quarterly Review (Q2 FY24)
7 | 8 | 9 | 10 | 11 | 12 | 13 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | 2023-02-08 | Monthly Review (January)
14 | 15 | 16 | 17 | 18 | 19 | 20 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 2023-03-06 | Monthly Review (February)
21 | 22 | 23 | 24 | 25 | 26 | 27 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  |  | 2023-03-07 | LT Offsite - Q4 FY24 Planning
28 | 29 | 30 | 31 |  |  |  | 25 | 26 | 27 | 28 | 29 |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  | 3/11-3/22 | Q4 FY24 Planning
[14 empty] | 24: 31 |  |  | 2023-03-28 | Quarterly Planning Review
April | [6 empty] | May | [6 empty] | 24: June | Out of Office/Vacation |  | Important Dates |  | Notes/Revisions
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |  |  | 2023-04-04 | Quarterly Review (Q3 FY24)
| 1 | 2 | 3 | 4 | 5 | 6 |  |  |  | 1 | 2 | 3 | 4 | [9 empty] | 2023-05-09 | Monthly Review (April) | bar: 24; 30
7 | 8 | 9 | 10 | 11 | 12 | 13 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 2023-06-05 | Monthly Review (May)
14 | 15 | 16 | 17 | 18 | 19 | 20 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  |  | 4/22-5/24 | LT - Annual Planning
21 | 22 | 23 | 24 | 25 | 26 | 27 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  |  | 2023-06-06 | LT Offsite - Q1 FY25 Planning
28 | 29 | 30 |  |  |  |  | 26 | 27 | 28 | 29 | 30 | 31 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 |  |  | 6/10-6/21 | Q1 FY25 Planning
[14 empty] | 23: 30 |  |  | 2023-06-27 | Quarterly Planning Review
Legend
Non-Working Day
Holiday
Pre-Read Sent (T-3)
Topics Sent (T-1)
Monthly Review Mtg
Quarterly Review Mtg
LT Offsite - Planning
Quarterly Planning - Dept
Planning Review

## FY23 ROB (hidden)
Viva Goals FY23 Rhythm of Business
[9 empty] | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
|  | Meeting | Audience | Audience Size | Owner | Complexity Size | Freqency | Source Calendar | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
GLOBAL EVENTS
HOLIDAYS
APAC
EMEA
| US | [7 empty] | 2023-01-01: 1/2: New Year's 1/16: MLK Day; 2023-02-01: 2/20: President's Day; 2023-05-01: 5/29: Memorial Day
GLOBAL
VIVA GOALS
Viva Goals Employee Engagment Events & Resource Groups
Viva Goals All Hands
Viva Goals ROB (Updated Quarterly)
|  | Viva Goals LT Offsite | [6 empty] | 2022-12-01: 2023-12-15; 2023-03-01: 2023-03-30; 2023-06-01: 2023-06-29
LT OKR Planning
Department OKR Planning
Monthly Review
|  | Quarterly Closeout | [6 empty] | 2022-10-01: 2023-10-06; 2023-01-01: 2023-01-04; 2023-03-01: 2023-03-23
Quarterly Retrospective
E+D
E+D Employee Engagement Events
E+D All Hands
E+D Ask Me Anything
Training
Standards of Business Conduct
Strike / Foundations
|  | Privacy 101 | ALL
E+D LT ROB (Updated Quarterly)
MICROSOFT EVENTS
Hackathon (internal)
Satya Q&A (internal)
Give/Day of Service (internal)
Inspire (external)
Microsoft Ready
Envision (external)
Ignite (external)
Microsoft Build (external)
Ability Summit (internal)
Grace Hopper
MS Poll
INDUSTRY EVENTS
|  | CES ¦ Consumer Eletronics | [6 empty] | 2023-01-01: 1/5-1/8